MFHS  Baptism Project

The Malvern Family History Society with 30 volunteers is currently transcribing Worcestershire Baptisms from the Parish Registers. We have chosen to do Baptism records as indexes are available for Worcestershire Marriages and Burials  but not for many Baptisms. Our project transcriptions are published on http://www.fhs-online.co.uk/ filling a gap in the research tools available to genealogists worldwide. Marriage & Burial transcriptions are being added by S&N to the above site. See http://www.mfhs.org.uk/  Project tab for updates on progress.

There are some 200 parishes in Worcestershire and the project has been split into 3 phases:

Phase 1 1813 to 1839. This phase is complete for 197 parishes 

Phase 2 1754 to 1812 Work on this phase started in 2009.  Currently 55 parishes completed.

Phase 3 1753 and back to start of registers, hopefully all complete by 2016.

Please contact me on Anthony.luffman@talktalktalk.net if you would like more information.

